## Sheet1
Task | Estimate | Actual | In progress | Status | Risks
Btn setup | 2 hrs | 4hr/4hr | Y | Complete | low | Both button have been done
Slider setup | 3 hrs | 2hr |  | Complete | low
Timer setup | 2 hrs | 1hr | Y | complete | low | Done
ITC setup | 3hr | 1hr | Y | complete | low | Done
slider monitor | 10hr | 2hr |  | Complete | mid | Done
Physics task | 10hr | 6hr | Y | Complete | Mid | Done
lcd task | 5hr | 4hr/4hr | Y | Complete | Mid | Finished
led task | 2 hrs |  |  | Incomplete | low
slider operator | 5hr | 3hr | Y | Complete | High | Done
shield task | 5hr | 2hr/4hr | Y | Complete | High | Done
Finish the game, | 3hr | 3hr |  | Complete | Mid
47hr