## Sheet1
Task | Estimate | Actual | In progress | Status | Risks | Roam
Btn setup | 2 hrs | 2hr/4hr | Y | Half-way done | low | Owned | Half-way done. Finish the Btn0 setup, including calculation of arming time and recharge time
Slider setup | 3 hrs |  |  | Incomplete | low | Owned
Timer setup | 2 hrs | 1hr | Y | complete | low | Owned | Finish the setup of timer for physics task, arming task, recharge task and
ITC setup | 3hr |  | Y | complete | low | Owned | Finish the setup of current ITC I have
slider monitor | 10hr |  |  | Incomplete | mid | Owned
Physics task | 10hr |  |  | Incomplete | High | Owned
lcd task | 5hr | 1hr/4hr |  | Incomplete | High | Owned | Play around with LCD and movement of platform and mass. But more realistic data are neeeded to test.
led task | 2 hrs |  |  | Incomplete | low | Owned
slider operator | 5hr |  |  | Incomplete | High | Owned
shield task | 5hr |  |  | Incomplete | High | Owned
47hr