## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Btn setup | 1 | 40 | 40 | 2022-03-10 |  | M | Mitigated, I didn't solve the laser button yet
Slider setup | 13 | 40 | 520 | 2022-03-10 |  | M | Mitigated, I didn't solve rebounce from canyon wall yet
Timer setup | 1 | 13 | 13 | 2022-03-10 |  | R | Resolved
ITC setup | 1 | 40 | 40 | 2022-03-10 |  | R | Resolved
slider monitor | 70 | 20 | 1400 | 2022-03-10 |  | R | Resolved
Physics task | 100 | 100 | 10000 | 2022-03-10 |  | M | I have some unit tests for it
lcd task | 100 | 100 | 10000 | 2022-03-10 |  | M | Plan aound with it, but lacking of real experiment data
led task | 40 | 40 | 1600 | 2022-03-10 |  | O | didn't start yet
slider operator | 70 | 70 | 4900 | 2022-03-10 |  | R | Resolved
shield task | 100 | 70 | 7000 | 2022-03-10 |  | R | Resolved
Data structure setup | 1 | 1 | 1 | 2022-03-15 |  | R | Resolved
Bounce from the wall | 40 | 100 | 4000 | 2022-03-15 |  | O | Just find it
Ball position calculation | 70 | 100 | 7000 | 2022-03-15 |  | O | Just find it
platform position calulation | 70 | 100 | 7000 | 2022-03-15 |  | M | I have unit test for position change
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100