## Sheet1
Task | Estimate | Actual | In progress | Status | Risks
Btn setup | 2 hrs | 2hr/4hr | Y | Half-way done | low | Half-way done. Finish the Btn0 setup, including calculation of arming time and recharge time
Slider setup | 3 hrs | 2 |  | Complete | low
Timer setup | 2 hrs | 1hr | Y | complete | low | Finish the setup of timer for physics task, arming task, recharge task and
ITC setup | 3hr |  | Y | complete | low | Finish the setup of current ITC I have
slider monitor | 10hr |  |  | Half-way done | mid | I haven't applied the real-world physics on it
Physics task | 10hr | 2hr |  | Incomplete | High | I have created some unit tests for it
lcd task | 5hr | 1hr/4hr |  | Half-way done | High | Play around with LCD and movement of platform and mass. But more realistic data are neeeded to test.
led task | 2 hrs |  |  | Incomplete | low
slider operator | 5hr | 3hr |  | Complete | High
shield task | 5hr | 2hr/4hr |  | Complete | High
47hr